## Task Sheet
SUMMARY | Total Tasks: 30
Task ID | Task Name | Category | Description | Assigned To | Start Date | End Date | Duration | Status | Priority | Dependencies | Notes
T-001 | Define project scope | Planning | Define objectives, hardware and software components | Student | 2026-01-05 | 2026-01-09 | 5 | Completed | High | — | Initial scoping
T-002 | Literature review on AMS | Planning | Research altitude sickness symptoms and detection methods | Student | 2026-01-10 | 2026-01-16 | 7 | Completed | High | T-001 | WHO and HRA guidelines reviewed
T-003 | System architecture design | Planning | Design overall system: ESP32 → Flask → Mobile app | Student | 2026-01-17 | 2026-01-23 | 7 | Completed | High | T-002 | —
T-004 | Select ML algorithm | Planning | Evaluate Decision Tree vs other classifiers for AMS risk | Student | 2026-01-24 | 2026-01-28 | 5 | Completed | High | T-003 | Decision Tree selected
T-005 | Procure hardware components | Hardware | Order ESP32, MAX30102, BMP180, OLED, buzzer, button | Student | 2026-01-29 | 2026-02-04 | 7 | Completed | High | T-003 | —
T-006 | Wire ESP32 circuit | Hardware | Connect sensors via I2C; buzzer GPIO 25; button GPIO 32 | Student | 2026-02-05 | 2026-02-07 | 3 | Completed | High | T-005 | Breadboard prototype
T-007 | Validate sensor readings | Hardware | Test raw SpO2, HR, altitude output values | Student | 2026-02-08 | 2026-02-11 | 4 | Completed | High | T-006 | Serial monitor used
T-008 | Implement SpO2 & HR reading | Firmware | Integrate MAX30102 library, read and average BPM/SpO2 | Student | 2026-02-12 | 2026-02-17 | 6 | Completed | High | T-007 | —
T-009 | Implement altitude reading | Firmware | Integrate BMP180, convert pressure to altitude in metres | Student | 2026-02-12 | 2026-02-14 | 3 | Completed | High | T-007 | —
T-010 | OLED display layout | Firmware | Design two-screen display: HR view and Altitude view | Student | 2026-02-15 | 2026-02-18 | 4 | Completed | Medium | T-008 | Button toggles screens
T-011 | Buzzer alert logic | Firmware | Trigger buzzer on High/Severe AMS risk | Student | 2026-02-19 | 2026-02-21 | 3 | Completed | Medium | T-010 | —
T-012 | WiFi & HTTP POST to Flask | Firmware | Send JSON sensor data to /predict every 1.5 seconds | Student | 2026-02-22 | 2026-02-26 | 5 | Completed | High | T-011 | HTTPClient library
T-013 | Set up Flask project | Backend | Create Flask app, install dependencies, configure routes | Student | 2026-02-05 | 2026-02-07 | 3 | Completed | High | T-004 | —
T-014 | Design SQLite schema | Backend | Create users and predictions tables with migrations | Student | 2026-02-08 | 2026-02-10 | 3 | Completed | High | T-013 | —
T-015 | Build auth endpoints | Backend | Implement /auth/register and /auth/login with tokens | Student | 2026-02-11 | 2026-02-14 | 4 | Completed | High | T-014 | —
T-016 | Train Decision Tree model | Backend | Train AMS risk classifier on altitude/SpO2/HR dataset | Student | 2026-02-15 | 2026-02-20 | 6 | Completed | High | T-015 | scikit-learn
T-017 | Build /predict endpoint | Backend | Accept sensor JSON, run ML model, return risk + recommendation | Student | 2026-02-21 | 2026-02-24 | 4 | Completed | High | T-016 | —
T-018 | Build /history endpoints | Backend | GET history, GET latest, DELETE history with auth | Student | 2026-02-25 | 2026-02-27 | 3 | Completed | Medium | T-017 | —
T-019 | Set up Expo project | Mobile App | Init React Native + Expo Router, install dependencies | Student | 2026-02-10 | 2026-02-12 | 3 | Completed | High | T-013 | —
T-020 | Build Login & Register screens | Mobile App | Implement auth screens with Spotify-style design, log.png hero | Student | 2026-02-13 | 2026-02-18 | 6 | Completed | High | T-019 | —
T-021 | Build Welcome screen | Mobile App | Animated welcome screen with mountain image | Student | 2026-02-19 | 2026-02-20 | 2 | Completed | Low | T-020 | —
T-022 | Build Track/Monitor tab | Mobile App | Live SpO2, HR, altitude display with elevation animation | Student | 2026-02-21 | 2026-03-05 | 13 | Completed | High | T-017 | Results screen after reading
T-023 | Build History tab | Mobile App | Line chart (altitude), donut chart (risk), entry cards | Student | 2026-03-06 | 2026-03-12 | 7 | Completed | High | T-018 | —
T-024 | Build Explore tab | Mobile App | Trek/hike listings, draggable detail sheet, Start Monitoring | Student | 2026-03-13 | 2026-03-22 | 10 | Completed | Medium | T-019 | Weather API integrated
T-025 | Build Profile tab | Mobile App | User profile display and logout | Student | 2026-03-23 | 2026-03-25 | 3 | Completed | Low | T-015 | —
T-026 | Unit test Flask endpoints | Testing | Test /predict /auth /history with sample data | Student | 2026-03-26 | 2026-03-30 | 5 | Completed | High | T-018 | Postman used
T-027 | Integration test ESP32↔Flask | Testing | Verify end-to-end: sensor read → POST → prediction stored | Student | 2026-03-31 | 2026-04-04 | 5 | Completed | High | T-026 | —
T-028 | Mobile app testing | Testing | Test all screens, navigation, offline behaviour | Student | 2026-04-05 | 2026-04-10 | 6 | In Progress | High | T-027 | —
T-029 | Write installation guidance | Documentation | Document hardware wiring, Flask setup, Expo setup steps | Student | 2026-04-11 | 2026-04-15 | 5 | In Progress | High | T-028 | —
T-030 | Complete project report | Documentation | Compile all project documents for evaluation submission | Student | 2026-04-16 | 2026-04-30 | 15 | In Progress | High | T-029 | —

## Resource Sheet
Resource ID | Resource Name | Resource Type | Specification / Role | Quantity | Est. Cost (USD) | Notes
R-001 | Student Developer | Human | Full-stack developer: firmware, backend, mobile app | 1 | 0 | Self-developed project
R-002 | Project Supervisor | Human | Academic supervisor providing guidance and evaluation | 1 | 0 | —
R-003 | ESP32 DevKit V1 | Hardware | Dual-core MCU, WiFi/BT, 30 GPIO pins | 1 | 5 | Main microcontroller
R-004 | MAX30102 Sensor | Hardware | Heart rate + SpO2 pulse oximeter; I2C interface | 1 | 3.5 | Connected via SDA/SCL
R-005 | BMP180 Sensor | Hardware | Barometric pressure + temperature → altitude; I2C | 1 | 2 | Altitude calculation
R-006 | SSD1306 OLED Display | Hardware | 128×64 pixel I2C OLED display | 1 | 4 | Shows HR / altitude
R-007 | Active Buzzer | Hardware | 5V active piezo buzzer; GPIO 25 | 1 | 0.5 | Alert on High/Severe risk
R-008 | Push Button | Hardware | Tactile momentary switch; GPIO 32 (INPUT_PULLUP) | 1 | 0.2 | Toggle display screen
R-009 | Breadboard | Hardware | 830-point solderless breadboard | 1 | 2 | Prototyping
R-010 | Jumper Wires | Hardware | Male-to-male and male-to-female 20cm wires | 30 | 1.5 | Connections
R-011 | USB Cable (Micro) | Hardware | Data + power cable for ESP32 programming | 1 | 1 | Arduino IDE upload
R-012 | Android / iOS Device | Hardware | Smartphone to run the Expo mobile app | 1 | 0 | Student's own device
R-013 | Laptop / PC | Hardware | Development machine for coding and running Flask server | 1 | 0 | Student's own device
R-014 | Arduino IDE | Software | v2.x — ESP32 firmware development and upload | 1 | 0 | Free
R-015 | Python 3.11 | Software | Backend runtime; Flask, scikit-learn, pandas | 1 | 0 | Open source
R-016 | Flask 3.x | Software | Lightweight REST API framework for Python | 1 | 0 | Open source
R-017 | scikit-learn | Software | Decision Tree ML classifier for AMS risk prediction | 1 | 0 | Open source
R-018 | SQLite | Software | Embedded relational database (ams_readings.db) | 1 | 0 | Built into Python
R-019 | Node.js 20.x | Software | JavaScript runtime for React Native / Expo toolchain | 1 | 0 | Open source
R-020 | React Native / Expo SDK 52 | Software | Cross-platform mobile app framework | 1 | 0 | Open source
R-021 | VS Code | Software | Primary code editor with ESLint, Python extensions | 1 | 0 | Free
R-022 | GitHub | Software | Version control and source code repository | 1 | 0 | Free tier
R-023 | draw.io | Software | ERD, EEERD, Use Case diagram creation | 1 | 0 | Free web tool
R-024 | Postman | Software | REST API testing tool for Flask endpoints | 1 | 0 | Free tier
TOTAL |  |  | Total Estimated Hardware Cost

## Requirement Catalogue
Req ID | Type | Requirement Description | Priority (MoSCoW) | Source | Status | Notes
FR-01 | FR | The system shall allow a new user to register with a username, email, and password | Must Have | User | Implemented | Validated via /auth/register
FR-02 | FR | The system shall allow a registered user to log in and receive an auth token | Must Have | User | Implemented | JWT-style token stored in app
FR-03 | FR | The system shall allow a logged-in user to log out and invalidate their token | Should Have | User | Implemented | Token set NULL in DB
FR-04 | FR | The ESP32 shall read SpO2 percentage from the MAX30102 sensor in real time | Must Have | Hardware | Implemented | Averaged over 4 readings
FR-05 | FR | The ESP32 shall read heart rate (BPM) from the MAX30102 sensor in real time | Must Have | Hardware | Implemented | —
FR-06 | FR | The ESP32 shall read current altitude in metres from the BMP180 sensor | Must Have | Hardware | Implemented | Derived from pressure reading
FR-07 | FR | The ESP32 shall display live readings on the OLED screen | Must Have | Hardware | Implemented | Toggles HR / Altitude view
FR-08 | FR | The ESP32 shall POST sensor data to the Flask /predict endpoint every ~1.5 seconds | Must Have | Hardware | Implemented | HTTPClient over WiFi
FR-09 | FR | The Flask API shall accept sensor data and return an AMS risk level and recommendation | Must Have | System | Implemented | Decision Tree ML model
FR-10 | FR | The system shall classify AMS risk into four levels: Low, Medium, High, Severe | Must Have | System | Implemented | Based on SpO2/HR/altitude
FR-11 | FR | The Flask API shall store every prediction in the SQLite database linked to the user | Must Have | System | Implemented | predictions table
FR-12 | FR | The mobile app shall display live SpO2, heart rate, and altitude during a monitoring session | Must Have | User | Implemented | Track tab
FR-13 | FR | The mobile app shall show a results screen with ECG, BPM, HRV, altitude and SpO2 after a session ends | Should Have | User | Implemented | Auto-triggered on idle
FR-14 | FR | The mobile app shall display the history of past predictions with charts | Should Have | User | Implemented | History tab: altitude line + risk donut
FR-15 | FR | The mobile app shall allow the user to explore trekking routes with trek details | Should Have | User | Implemented | Explore tab with detail sheet
FR-16 | FR | Clicking Start Monitoring from a trek detail shall navigate to the Track tab | Should Have | User | Implemented | router.push('/(tabs)/track')
FR-17 | FR | The buzzer shall sound an alert when the AMS risk level is High or Severe | Must Have | Hardware | Implemented | GPIO 25 active buzzer
FR-18 | FR | The system shall allow the user to clear their prediction history | Could Have | User | Implemented | DELETE /history endpoint
NFR-01 | NFR | The Flask API shall respond to /predict requests within 2 seconds under normal WiFi conditions | Must Have | Performance | Validated | Tested on LAN
NFR-02 | NFR | The mobile app shall load each screen within 1.5 seconds on a mid-range Android device | Should Have | Performance | In Progress | —
NFR-03 | NFR | The AMS risk classification shall achieve at least 85% accuracy on the test dataset | Must Have | Accuracy | Validated | Decision Tree trained on labelled data
NFR-04 | NFR | The system shall operate reliably on a local WiFi network without internet access | Must Have | Availability | Implemented | Flask runs on local IP
NFR-05 | NFR | User passwords shall be stored as hashed values in the database | Must Have | Security | Implemented | Not plain text
NFR-06 | NFR | All API endpoints (except /auth) shall require a valid token for access | Should Have | Security | Implemented | Bearer token validation
NFR-07 | NFR | The mobile app shall be compatible with Android 10+ and iOS 14+ | Should Have | Portability | In Progress | Expo SDK 52 targets both